## Product Backlog
Product Backlog
ID | User Story | Assigned To | Sprint | Priority | Story Points | Status
1 | Conduct Site Survey | Project Manager | 1 | High | 2 | Done
2 | Obtain Necessary Permits and Approvals | Legal Expert | 1 | High | 5 | Done
3 | Clear and Prepare Site | Site Superviser | 1 | High | 8 | In Progress
4 | Install Underground Storage Tanks (USTs) | Tank Installation Specialist | 1 | High | 8 | In Progress
5 | Construct Fuel Dispensers | Equipment Specialist | 2 | Medium | 5 | In Progress
6 | Lay Fuel Pipes and Connections | Plumbing Expert | 2 | Medium | 5 | Done
7 | Construct Office Building | Construction Foreman | 2 | Low | 8 | In Progress
8 | Install POS Systems and Payment Terminals | IT Specialist | 2 | High | 3 | Not Started
9 | Construct Canopy and Forecourt | Construction Engineer | 3 | Medium | 8 | In Progress
10 | Install CCTV and Surveillance Systems | Security System Expert | 3 | Low | 3 | On Hold
11 | Implement Fire Suppression Systems | Safety System Expert | 3 | High | 5 | In Progress
12 | Set Up Backup Power Systems (UPS) | Electrical Engineer | 4 | High | 3 | In Progress
13 | Install Spill Containment Systems | Enviromental Specialist | 4 | Medium | 3 | Not Started
14 | Construct Driveways and Parking Areas | Construction Superviser | 4 | Low | 5 | On Hold
15 | Install Digital Signage | Digital Signage Expert | 5 | Low | 5 | In Progress
16 | Landscaping and Aesthetic Improvements | Landscaping Contractor | 5 | Low | 3 | Overdue
17 | Conduct Quality Inspection and Testing | QA Engineer | 6 | Medium | 5 | In Progress
18 | Finalize and Clean Up Site | Construction Superviser | 6 | Medium | 3 | In Progress
19 | Conduct Training for Staff on New Facilities | Training Coordinator | 7 | Medium | 8 | Done
20 | Integrate Fuel Management System with Infrastructure | IT Specialist | 7 | High | 8 | In Progress
21 | Obtain Final Regulatory Approval | Regulatory Compliance Expert | 8 | Medium | 5 | In Progress
22 | Conduct Soft Launch and Initial Operations | Project Manager | 8 | High | 8 | In Progress

## Cost Estimation
Total Estimated Cost
Cost Category | Estimated Low (INR) | Estimated High (INR) | % Against Total Cost (Low) | % Against Total Cost (High)
Land Acquisition | 4000000 | 6000000 | 26.85% | 25.1%
Construction Costs | 5000000 | 9000000 | 33.56% | 37.66%
Equipment Costs | 2500000 | 3200000 | 16.78% | 13.39%
Regulatory and Permitting Costs | 800000 | 1500000 | 5.369% | 6.276%
Operational Costs | 1000000 | 1500000 | 6.711% | 6.276%
Marketing and Branding | 200000 | 500000 | 1.342% | 2.092%
Contingency Fund | 1400000 | 2200000 | 9.396% | 9.205%
Total Estimated Cost | 14900000 | 23900000 | 100% | 100%

## Sprint 1
Sprint 1 - Initiation and Site Preparation
Project Name |  | Project Manager | Start Date | Finish Date | Overall Progress | Total Duration | Total Story Points
Petrol Pump Development |  | Ashwini Bagde | 2025-03-01 | 2025-03-14 | 85% | 24 | 23
ID | Task | Feature type | Responsible | Story Points | Start Date | Finish Date | Duration (in days) | Status | Priority | Task Completion % | Comments
1 | Conduct Site Survey | Site Preparation | Ashwini | 2 | 2025-03-01 | 2025-03-03 | 3 | Done | High | 100% | Initial site assessment
2 | Obtain Necessary Permits and Approvals | Regulatory | Anita | 5 | 2025-03-01 | 2025-03-07 | 5 | Done | High | 100% | Legal compliance
3 | Clear and Prepare Site | Site Preparation | Manoj | 8 | 2025-03-04 | 2025-03-10 | 7 | In progess | High | 80% | Site clearance
4 | Install Underground Storage Tanks (USTs) | Infrastructure | Ashok | 8 | 2025-03-08 | 2025-03-15 | 9 | In Progress | High | 60% | Tank installation

## Sprint 2
Sprint 2 - Foundation and Infrastructure Setup
Project Name |  | Project Manager | Start Date | Finish Date | Overall Progress | Total Duration | Total Story Points
Petrol Pump Development |  | Ashwini Bagde | 2025-03-15 | 2025-03-26 | 67.5% | 31 | 21
ID | Task | Feature type | Responsible | Story Points | Start Date | Finish Date | Duration (in days) | Status | Priority | Task Completion % | Comments
5 | Construct Fuel Dispensers | Infrastructure | Priya | 5 | 2025-03-15 | 2025-03-21 | 7 | In Progress | Medium | 90% | Fuel dispensers setup
6 | Lay Fuel Pipes and Connections | Infrastructure | Rakesh | 5 | 2025-03-16 | 2025-03-22 | 7 | Done | Medium | 100% | Pipe laying and connection
7 | Construct Office Building | Building | Suresh | 8 | 2025-03-15 | 2025-03-28 | 13 | In Progress | Low | 80% | Office construction
8 | Install POS Systems and Payment Terminals | Technology | Meera | 3 | 2025-03-23 | 2025-03-26 | 4 | Not Started | High | 0% | Payment systems setup

## Sprint 3
Sprint 3 - Canopy, Forecourt, and Safety Systems
Project Name |  | Project Manager | Start Date | Finish Date | Overall Progress | Total Duration | Total Story Points
Petrol Pump Development |  | Ashwini Bagde | 2025-03-29 | 2025-04-11 | 67.33% | 22 | 16
ID | Task | Feature type | Responsible | Story Points | Start Date | Finish Date | Duration (in days) | Status | Priority | Task Completion % | Comments
9 | Construct Canopy and Forecourt | Infrastructure | Vinay | 8 | 2025-03-29 | 2025-04-11 | 13 | In Progress | Medium | 70% | Canopy and forecourt setup
10 | Install CCTV and Surveillance Systems | Security | Arjun | 3 | 2025-04-01 | 2025-04-04 | 4 | On Hold | Low | 52% | CCTV installation
11 | Implement Fire Suppression Systems | Safety | Deepak | 5 | 2025-04-05 | 2025-04-09 | 5 | In Progress | High | 80% | Fire Suppression setup
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.

## Sprint 4
Sprint 4 - Backup Systems and Containment
Project Name |  | Project Manager | Start Date | Finish Date | Overall Progress | Total Duration | Total Story Points
Petrol Pump Development |  | Ashwini Bagde | 2025-04-12 | 2025-04-20 | 53.17% | 15 | 11
ID | Task | Feature type | Responsible | Story Points | Start Date | Finish Date | Duration (in days) | Status | Priority | Task Completion % | Comments
12 | Set Up Backup Power Systems (UPS) | Technology | Sameer | 3 | 2025-04-12 | 2025-04-14 | 3 | In Progress | High | 77% | UPS setup
13 | Install Spill Containment Systems | Safety | Ravi | 3 | 2025-04-15 | 2025-04-17 | 3 | Not Started | Medium | 0% | Spill Containment
14 | Construct Driveways and Parking Areas | Infrastructure | Ajay | 5 | 2025-04-12 | 2025-04-20 | 9 | On Hold | Low | 82.5% | Driveways and Parking

## Sprint 5
Sprint 5 - Digital Signage and Aesthetic Improvements
Project Name |  | Project Manager | Start Date | Finish Date | Overall Progress | Total Duration | Total Story Points
Petrol Pump Development |  | Ashwini Bagde | 2025-04-21 | 2025-05-05 | 56.5% | 10 | 8
ID | Task | Feature type | Responsible | Story Points | Start Date | Finish Date | Duration (in days) | Status | Priority | Task Completion % | Comments
15 | Install Digital Signage | Technology | Nisha | 5 | 2025-04-21 | 2025-04-28 | 5 | In Progress | Low | 52% | Digital Signage setup
16 | Landscaping and Aesthetic Improvements | Aesthetic | Sanjay | 3 | 2025-04-29 | 2025-05-05 | 5 | Overdue | Low | 61% | Landscaping and Aesthetic

## Sprint 6
Sprint 6 - Quality Inspection and Testing
Project Name |  | Project Manager | Start Date | Finish Date | Overall Progress | Total Duration | Total Story Points
Petrol Pump Development |  | Ashwini Bagde | 2025-05-10 | 2025-05-18 | 51.75% | 9 | 8
ID | Task | Feature type | Responsible | Story Points | Start Date | Finish Date | Duration (in days) | Status | Priority | Task Completion % | Comments
17 | Conduct Quality Inspection and Testing | Quality | Pooja | 5 | 2025-05-10 | 2025-05-14 | 5 | In Progress | Medium | 71% | Quality inspection
18 | Finalize and Clean Up Site | Cleanup | Vikram | 3 | 2025-05-15 | 2025-05-18 | 4 | In Progress | Medium | 32.5% | Final cleanup

## Sprint 7
Sprint 7 - Integration and Training
Project Name |  | Project Manager | Start Date | Finish Date | Overall Progress | Total Duration | Total Story Points
Petrol Pump Development |  | Ashwini Bagde | 2025-05-20 | 2025-06-06 | 76% | 12 | 16
ID | Task | Feature type | Responsible | Story Points | Start Date | Finish Date | Duration (in days) | Status | Priority | Task Completion % | Comments
19 | Conduct Training for Staff on New Facilities | Training | Kiran | 8 | 2025-05-20 | 2025-05-28 | 8 | Done | Medium | 100% | Staff training
20 | Integrate Fuel Management System with Infrastructure | Integration | Meera | 8 | 2025-05-29 | 2025-06-06 | 4 | In Progress | High | 52% | System integration
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.

## Sprint 8
Sprint 8 - Final Approvals and Launch
Project Name |  | Project Manager | Start Date | Finish Date | Overall Progress | Total Duration | Total Story Points
Petrol Pump Development |  | Ashwini Bagde | 2025-06-07 | 2025-06-20 | 17% | 17 | 13
ID | Task | Feature type | Responsible | Story Points | Start Date | Finish Date | Duration (in days) | Status | Priority | Task Completion % | Comments
21 | Obtain Final Regulatory Approval | Regulatory | Anjali | 5 | 2025-06-07 | 2025-06-13 | 8 | In Progress | Medium | 34% | Final approval
22 | Conduct Soft Launch and Initial Operations | Launch | Project Team | 8 | 2025-06-12 | 2025-06-20 | 9 | In Progress | High | 0% | Soft launch and initial operations

## Dropdown List
Dropdown List
Priority | Status | Responsible Person
High | Done | Ashwini
Medium | In Progress | Anita
Low | Not Started | Manoj
| On Hold | Ashok
| Overdue | Priya
Rakesh
Suresh
Meera
Vinay
Arjun
Deepak
Sameer
Ravi
Ajay
Nisha
Sanjay
Pooja
Vikram
Kiran
Meera
Anjali
Project Team